## Sheet1
Sample Risk Management Register for Project XXXX
Risk Identification |  |  | Qualitative Risk Assessment | [8 empty] | Risk Response Plan |  | Monitoring and Control
# | Category | Risk Description | Probability | Impact | Risk Matrix | [6 empty] | Response Strategy | Response Actions | Responsibile Entity | Status: Date and Review Comments
1 | Ethical | Data Poisoning | M | H | Probability | VH | [5 empty] | Manage 2.4 (NIST AIRC): Ensure halt mechanisms are in place when there are signs of data poisoning. Next, Investigate data to trace models lineage back to the particular dataset that is corrupted. This should be prioritized due to high impact. | 1. Ensure halt/containment of model. 2. Then investigate and correct poisoned dataset. 3. Bring model back online once validated and retested. | Security Engineer or AI Security Engineer | Status: Risk is not actively happening. -Last Review Date: 09/06/2026 -Comments: Medical LLMs are vulnerable to data poisoning attacks. The risk matrix was marked at medium probability and high impact. The probability is medium due to Google’s strict controls on current models in use by medical companies.
H
[6 empty] | M |  |  |  | X
|  | APPENDIX A: Option 2 (Healthcare Provider) The best AI model for healthcare imaging is provided by google.Their foundation model is the MedLM hosted on the cloud (Google cloud Vertex AI). Other models include MedGemma for image and text comprehension. And Med-PaLM for clinical reasoning and diagnostic dialogues. Data poisoning is training data becoming corrupt due to attacker feeding it malicious, incorrect, or biased data during the learning phase. This risk could corrupt the information systems and models used for patients. |  |  |  | L
VL
|  | Risk Description: MedLM utilizing internet data that could have deliberte wrong information making the output or certain increments of the output corrupt. This could lead to harmful medical advice, wrong diagnoses to patients, and incorrect EHR records. This would impact the business credability and would be non-compliant with HIPAA. |  |  |  |  | VL | L | M | H | VH
Impact
2 | Legal | Harmful Human AI Configuration | H | VH | Probability | VH | [5 empty] | Govern 3.2(NIST AIRC): Implement policies and procedures such as AI incident and error report procedures(Manage 4.3). Create procedures for authorized medical roles making human-AI configurations. Create data privacy policy on data access and patient consent for various models such as MedGemma, Med-PaLM, and MedLM. | 1. Regular meetings with authorized medical professionals who make human-AI changes. 2. Create dashboard for AI incident and error report tickets to manage. 3. Consistent mandatory training on human-AI configurations for authorized personnel and the impact it could have. | Licensed Medical Staff | -Status: No current tickets open regarding harmful AI incidents. -Last Review Date: 09/06/2026 -Comments: Harmful human AI configuration probability was set to high due to AI’s usage growing faster than legal frameworks for AI. The impact is very high due to the legal impact, medical board revoking licenses, and medical company reputation.
[6 empty] | H |  |  |  |  | X
|  | Medical companies are being held legally accountable for AI configurations they don’t completely understand. Medical boards are mandating that licensed professionals take full accountability for using, accepting, and rejecting AI’s output or recommendations. |  |  |  | M
L
|  | Risk Description: Unauthorized medical personnel including system administrators making changes, adaptions, and configurations to MedPaLM and MedGamma can create significant clinical, compliance, and also technical issues. Misconfigurations for these medical AI platforms can lead to changes in safety guardrails and patient data can be compromised. Fine-tuning also happens when AI changes are made, this could lead to non-standard or biased data being used by the model to make decisions. This would negatively impact the image outputs, EHR integrity, the patient, and could create technical issues for integration amoung MedPaLM/MedGamma and the company's CRM. Other systems unauthorized AI configurations could impact include: Paitent portal/messaging, AI analytics pipelines to the cloud infrastructure VertexAI, and misinterpretations of diagnostic scans (radiology communication). |  |  |  | VL
[7 empty] | VL | L | M | H | VH
Impact
3 | Technical | Cross-Modality Jailbreak Attack | H | VH | Probability | VH | [5 empty] | Ensure all models have adversarial training pre deployment. Measure 2.4 (NIST AIRC): Ensure continuous monitoring of image-text misconfigurations or input validations on each API call. |  | AI Engineer, Backend Engineer, DevOps Engineer | -Status: API calls are continuously monitored by AI engineer. -Last Review Date: 09/06/2026 -Comments: For a middle sized medical company with a focus on imagery. A cross-modality jailbreak should be set to very high impact. Due to API-integrated systems and cloud infrastructures being used the probability is set to high.
|  | Risk Description: Cross-modality jailbreak attack is a medical LLM issue that involves feeding a model a mismatched image-text pair. Such as text regarding lung X-ray to a image of an MRI brain scan. This causes misdiagnoses and could reveal sensitive information, violating HIPAA laws. Integrating medical LLMs with API-driven systems can create complex technical issues like cross-modality jailbreak. This causes harm to the patient and could be used for malicious intent. This can impact the business and patients receiving X-rays and MRIs. This risk can impact automated alerts within emergency systems, radiology work flow, and incorrect EHRs. This risk would also violate HIPAA laws and lower public trust within this healthcare imagery business. |  |  |  | H |  |  |  |  | X |  | 1. Create dashboard or alerts for continuous monitoring on API calls for input validations to ensure no cross-modality jailbreak. 2. Ensure weekly meetings among AI engineers and Backend/DevOps engineers to discuss potential integration issues to be proactive.
M
L
VL
[7 empty] | VL | L | M | H | VH
Impact
4 | Operational | Hallucinations | H | H | Probability | VH | [5 empty] | Implement the “no source, no output” policy for all AI models used. Map 1.6 (NIST AIRC): This pipeline was created to ensure every claim has evidence if the model can not retrieve said data then the output should be “I don’t know or I can not help”. | 1. Meet with AI Engineer to ensure the models MedLM and Med-PaLM have a “no source no output” requirement before deployment. | AI Engineer | -Status: Meeting set for 09/06 with AI Engineer -Last Review Date: 09/06/2026 -Comments: Impact for hallucinations set to high due to impacting various business departments and probability set to high as hallucinations is a top risk for AI currently.
|  | Risk Description: Hallucinations in AI LLMs are incorrect outputs that sound correct but could mislead clinical decisions. It is distorted information that is presented in a factual way. This could contradict traditional treatment, give unsafe outputs, or give wrong medical or non correlated protocols. This could also impact operations as the AI information stakeholders use to make decisions can be misleading. Other impacts include dashboard data, virtual assistant and agent output within MedLM, and analytical engines within MedLM. |  |  |  | H |  |  |  | X
M
L
VL
[7 empty] | VL | L | M | H | VH
5 | Privacy | Prohibited Direct Patient Use | M | H | Probability | VH | [5 empty] | Implement GOVERN 1.3 (NIST ARC): Define MedLM usage through policies. Strict policies include no patient should utilize MedLM or corresponding models to make decisions or self diagnose and should consult with a medical professional. | 1. Meet with AI engineer and software engineer to ensure 2FA for MedLM and Prohibited use notifications are in place for patients to agree to. | AI Security Engineer and Application or Java Engineer | -Status: 2FA is in place for utilizing MedLM internally and all patients must agree to AI usage and prohibited awareness within app.
|  | Google takes privacy concerns seriously when contracting with medical companies using MedLM. In the terms is states customers of medical company can not use MedLM. It's for internal use only. |  |  |  | H
[6 empty] | M |  |  |  | X
|  | Risk Description: Prohibited use of MedLM and related models by patients and non-medical experts can cause mis-judged urgency, lack of licensed judgement, and a wide range of health liabilities. This impact is regulatory and legal effecting the business through penalties and legal payouts. Another risk event event is misdiagnoses. This undesirable event can impact patients and disrupt radiology/nursing work flow. |  |  |  | L
VL
[7 empty] | VL | L | M | H | VH
6 | Technical | Model Depreciation | L | H | Probability | VH | [5 empty] | Manage 2.4 (NIST ARC): Is the best plan of action this risk. As Google does not have frequent depreciation the focus should be on managing to remove old model and integrate the new model for imaging decisions. Manage SLAs and monitoring metrics for third party under new model. | 1. Meet with AI Engineer and Google representitive to discuss ways to manage and integrate new model. 2. GRC analyst and third party vendors must communicate on changes regarding new model and accountability. | Google AI representative, AI Engineer, GRC analyst, Third party vendors | No new model from Google at this time.
H
M
|  | Risk Description: Google has had depreciation within their models in the past. Specifically tasks within MedLM were adopted by MedGemma. MedGemma becoming the lead model for clinical and financial work. Depreciation within models impact performance and technical aspects of the business. Unplanned migration for the new model can lead to API issues within Vertex AI cloud/MedGemma/company application and disrupted work flow for current model. Another impact is vendor gaps created with the new models. This would consist of training the new model on the accountability gap. |  |  |  | L |  |  |  | X
VL
[7 empty] | VL | L | M | H | VH
7 | Strategic | Heatmap for AI Mis-reads | M | H | Probability | VH | [5 empty] | Map 2.3 (NIST ARC): Best response would be to create scoring, parameters, and labels within MedGemma regarding reasons on why text outputs do not match image. Or why outputs are incorrect reported by medical staff. | 1. Meet with AI Engineer and Data Analyst regarding dashboard creation within MedGemma using Bigquery ML. 2. Use heatmap to monitor MedGemma incorrect outputs on patients. 3. Scheule monthly follow ups with AI Engineer on where within the Model we have the most issues and mitigation plan. | AI Engineer, Senior Management | Status: Monthly meetings creating within calendar regarding heatmap mis-reads
H
[6 empty] | M |  |  |  | X
|  | Risk Description: Utilizing a heatmap with categories and scorings made of why the models produced incorrect output of text and images is great risk to manage on a dashboard. Since this healthcare company specializes in imagery/radiology with AI integrated this would be a great strategic approach. The impact would be faster investigation and tuning for the current model. With indication of where to be proactive or mitigate within MedGemma. |  |  |  | L
VL
[7 empty] | VL | L | M | H | VH